## Master Plan
SSIS Development Plan
Fase | Server Source | Assignee | Timeline
Data Preparation
ETL1
ZPRUPF_V2 | GPDR | Frank Zhang | 7/31/2020 (Iteration 3)
AC1108RDB | GPDR | Frank Zhang | 7/31/2020 (Iteration 3)
AC1108RDR | GPDR | Frank Zhang | 7/31/2020 (Iteration 3)
IPSUPF | GPDR | Frank Zhang | 7/31/2020 (Iteration 3)
IPRVPF | GPDR | Frank Zhang | 7/31/2020 (Iteration 3)
GLISS_TBIILIFE_INSURED_FINAL | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_PRUAMAN_POLICY | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
OMNI_REPORT_PROPHET_CUSTOMER | DEV DATALAKE
IFRS17_PRUAMAN_SYARIAH | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_CREDIT_SHIELD | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17 (IFRS17_PRUEMAS) | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_CB_MAPPING | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_PORTFOLIO_MAPPING | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_ICG_CONFIG | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_SET_OF_CONTRACT | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3)
IFRS17_STATUS_MAPPING_TABLE | DEV DATALAKE | Frank Zhang | 7/31/2020 (Iteration 3) | table | day
ETL4 |  |  |  | 16
stg.acmvpf |  |  |  |  | 3
stg.rtrnpf
stg.gtrnpf
stg.genlpf
stg.chdrpf
stg.covrpf
stg.regppf
stg.clmhpf
stg.descpf
stg.covtpf
ifrs17_coa_inscope
ifrs17_param_table_mapping
ifrs17_param_table_mapping_nonrelated
ifrs17_cohort_mapping_table
tBiilife_Insured_Final | DEV DATALAKE | Frank Zhang | 2020-08-05
incoming_pd (Claim GLIS) | DEV DATALAKE | Frank Zhang | 2020-08-05
etl4_plai_sungl_mapping | DEV DATALAKE | Frank Zhang | 2020-08-05
MS_POLICY | DEV DATALAKE | Frank Zhang | 2020-08-05
MS_CLAIM | DEV DATALAKE | Frank Zhang | 2020-08-05
MS_POLICY_SHARIA | DEV DATALAKE | Frank Zhang | 2020-08-05
MS_CLAIM_SHARIA | DEV DATALAKE | Frank Zhang | 2020-08-05
MS_REFUND | DEV DATALAKE | Frank Zhang | 2020-08-05
billing_submission | DEV DATALAKE
billing_trx | DEV DATALAKE
premium_line | DEV DATALAKE
member_product | DEV DATALAKE
policy_member | DEV DATALAKE
member | DEV DATALAKE
person | DEV DATALAKE
product_option | DEV DATALAKE
product | DEV DATALAKE
customer_account | DEV DATALAKE
groups | DEV DATALAKE
policy | DEV DATALAKE
receipt_application | DEV DATALAKE
creditshield_premium | DEV DATALAKE | Frank Zhang | 2020-08-05
creditshield_claim | DEV DATALAKE | Frank Zhang | 2020-08-05
pruemas_premium | DEV DATALAKE | Frank Zhang | 2020-08-05
pruemas_claim | DEV DATALAKE | Frank Zhang | 2020-08-05
stg.ptrnpf
etl4_lifeasia
tmp.pdcnpf
tmp.prcnpf
TPA_source
stg.zdcvpf
renova_premium
renova_claim
stg.zngspf
stg.zgodpf
stg.agntpf
bank_charges_rate
stg.zrvhpf
stg.zglepf
stg.itempf
policy_adj_temp_source
etl4_lifeasia_nonrelated
ETL5
Data Ingestion
ETL1
ZPRUPF_V2 |  |  | 08/03/2020 - 08/7/2020
AC1108RDB |  |  | 08/03/2020 - 08/7/2020
AC1108RDR |  |  | 08/03/2020 - 08/7/2020
IPSUPF |  |  | 08/03/2020 - 08/7/2020
IPRVPF |  |  | 08/03/2020 - 08/7/2020
GLISS_TBIILIFE_INSURED_FINAL |  |  | 08/03/2020 - 08/7/2020
IFRS17_PRUAMAN_POLICY |  |  | 08/03/2020 - 08/7/2020
OMNI_REPORT_PROPHET_CUSTOMER
IFRS17_PRUAMAN_SYARIAH |  |  | 08/03/2020 - 08/7/2020
IFRS17_CREDIT_SHIELD |  |  | 08/03/2020 - 08/7/2020
IFRS17 (IFRS17_PRUEMAS) |  |  | 08/03/2020 - 08/7/2020
IFRS17_CB_MAPPING |  |  | 08/03/2020 - 08/7/2020
IFRS17_PORTFOLIO_MAPPING |  |  | 08/03/2020 - 08/7/2020
IFRS17_ICG_CONFIG |  |  | 08/03/2020 - 08/7/2020
IFRS17_SET_OF_CONTRACT |  |  | 08/03/2020 - 08/7/2020
IFRS17_STATUS_MAPPING_TABLE |  |  | 08/03/2020 - 08/7/2020
ETL4
stg.acmvpf
stg.rtrnpf
stg.gtrnpf
stg.genlpf
stg.chdrpf
stg.covrpf
stg.regppf
stg.clmhpf
stg.descpf
stg.covtpf
ifrs17_coa_inscope
ifrs17_param_table_mapping
ifrs17_param_table_mapping_nonrelated
ifrs17_cohort_mapping_table
tBiilife_Insured_Final |  |  | 8/6/2020 - 8/10/2020
incoming_pd (Claim GLIS) |  |  | 8/6/2020 - 8/10/2020
etl4_plai_sungl_mapping |  |  | 8/6/2020 - 8/10/2020
MS_POLICY |  |  | 8/6/2020 - 8/10/2020
MS_CLAIM |  |  | 8/6/2020 - 8/10/2020
MS_POLICY_SHARIA |  |  | 8/6/2020 - 8/10/2020
MS_CLAIM_SHARIA |  |  | 8/6/2020 - 8/10/2020
MS_REFUND |  |  | 8/6/2020 - 8/10/2020
billing_submission
billing_trx
premium_line
member_product
policy_member
member
person
product_option
product
customer_account
groups
policy
receipt_application
creditshield_premium |  |  | 8/6/2020 - 8/10/2020
creditshield_claim |  |  | 8/6/2020 - 8/10/2020
pruemas_premium |  |  | 8/6/2020 - 8/10/2020
pruemas_claim |  |  | 8/6/2020 - 8/10/2020
stg.ptrnpf
etl4_lifeasia
tmp.pdcnpf
tmp.prcnpf
TPA_source
stg.zdcvpf
renova_premium
renova_claim
stg.zngspf
stg.zgodpf
stg.agntpf
bank_charges_rate
stg.zrvhpf
stg.zglepf
stg.itempf
policy_adj_temp_source
etl4_lifeasia_nonrelated
ETL5
Transformation
ETL1
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_prophetu |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_proptrdb |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_proptrdr |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_resvpia |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_prophetu_pul |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_paylife |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_pruaman |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_omni |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_pruaman_syariah |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_credit_shield |  |  | 08/07/2020 - 08/21/2020
ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_pruemas |  |  | 08/07/2020 - 08/21/2020
ETL4
etl4_lifeasia
elt4_paylife |  |  | 8/10/2020 - 8/24/2020
etl4_pruaman |  |  | 8/10/2020 - 8/24/2020
el4_pruaman_syariah |  |  | 8/10/2020 - 8/24/2020
etl4_omni
etl4_pruemas |  |  | 8/10/2020 - 8/24/2020
etl4_creditshield |  |  | 8/10/2020 - 8/24/2020
etl4_gjrev
etl4_surrender_report
etl4_renova
ga_allowance
bank_charges_policy
etl4_lifeasia_missing
etl4_pat |  |  | 8/10/2020 - 8/24/2020
etl4_commission
Load

## ETL1 Plan
Iteration | Table | Source | Current Deliverable | Remarks
Iteration 1 | ZPRUPF_V2 | GPDR (SCHEMA TMP) | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_prophetu
| AC1108RDB |  | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_proptrdb
| AC1108RDR |  | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_proptrdr
| IPSUPF |  | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_resvpia
| IPRVPF |  | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_prophetu_pul
Iteration 2 | GLISS_TBIILIFE_INSURED_FINAL | Postgre (SCHEMA IFRS17) | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_paylife
| IFRS17_PRUAMAN_POLICY |  | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_pruaman
Iteration 3 | OMNI_REPORT_PROPHET_CUSTOMER | Postgre (SCHEMA IFRS17) | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_omni
Iteration 4 | IFRS17_PRUAMAN_SYARIAH | Postgre (SCHEMA IFRS17) | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_pruaman_syariah
Iteration 5 | IFRS17_CREDIT_SHIELD | Postgre(SCHEMA IFRS17) | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_credit_shield
Iteration 6 | IFRS17 (IFRS17_PRUEMAS) | Postgre (SCHEMA IFRS17) | ifrs17.ifrs17_dev_fnc_monthly_icg_mpfiles_pruemas
Iteration Config Table | IFRS17_CB_MAPPING IFRS17_PORTFOLIO_MAPPING IFRS17_ICG_CONFIG IFRS17_SET_OF_CONTRACT IFRS17_STATUS_MAPPING_TABLE | GP DR (SCHEMA IFRS17) & POSTGRES (SCHEMA IFRS17) | N/A | these tables are used as references.
Levelized Premium | STG.COVRPF STG.ZHSTPF STG.IHBPPF STG.IHBYPF STG.LIFEPF STG.LEXTPF STG.CHDRPF | GP DR (Schema STG) | ifrs17.ifrs17_levelized_check_alteration_function(date_parameter integer) ifrs17.ifrs17_basic_rider_new_business() ifrs17.ifrs17_levelized_history() --alteration main ifrs17.ifrs17_basic_rider_alteration(integer) --calculation phase 1 ifrs17.ifrs17_alteration_1_precalculation(integer) ifrs17.ifrs17_alteration_1_age_rider_health_calculation() ifrs17.ifrs17_alteration_1_sum_insured_calculation() ifrs17.ifrs17_alteration_1_premium_calculation() --premium phase 1 ifrs17.ifrs17_alteration_premium_2_basic() ifrs17.ifrs17_alteration_premium_3_prucrisis_cover() ifrs17.ifrs17_alteration_premium_4_prucrisis_cover_34() ifrs17.ifrs17_alteration_premium_5_prucrisis_cover_benefit_34() ifrs17.ifrs17_alteration_premium_6_prumultiple_crisis_cover() ifrs17.ifrs17_alteration_premium_7_pruearly_stage_crisis_cover() ifrs17.ifrs17_alteration_premium_8_pru_crisis_income() ifrs17.ifrs17_alteration_premium_9_prupersonal_accident_death() ifrs17.ifrs17_alteration_premium_10_prupersonal_accident_death_and_dis() ifrs17.ifrs17_alteration_premium_13_prumed() ifrs17.ifrs17_alteration_premium_14_pruhospital_and_surgical_idr() ifrs17.ifrs17_alteration_premium_14_pruhospital_and_surgical_usd() ifrs17.ifrs17_alteration_premium_15_pruhospital_and_surgical_75() ifrs17.ifrs17_alteration_premium_16_pruhospital_and_surgical_cover() ifrs17.ifrs17_alteration_premium_28_prujuvenile_crisis_cover() ifrs17.ifrs17_alteration_premium_30_prulink_term() ifrs17.ifrs17_alteration_premium_31_prupersonal_accident_death_plus() ifrs17.ifrs17_alteration_premium_32_prupersonal_accident_death_and_dis() ifrs17.ifrs17_alteration_premium_33_pruearly_stage_crisis_cover_plus() ifrs17.ifrs17_alteration_premium_34_pruhospital_and_surgical_cover_plu() ifrs17.ifrs17_alteration_premium_35_prumed_cover() ifrs17.ifrs17_alteration_premium_36_prucrisis_cover_benefit_plus_61() ifrs17.ifrs17_alteration_premium_41_pruprime_healthcare() ifrs17.ifrs17_alteration_premium_42_pruprime_healthcare_plus() ifrs17.ifrs17_alteration_premium_43_prucrisital_hospital_cover() ifrs17.ifrs17_alteration_premium_44_prutpd() ifrs17.ifrs17_alteration_premium_45_prutop_cica_ccb34() ifrs17.ifrs17_alteration_premium_46_prutop_cica_ccb61() ifrs17.ifrs17_alteration_premium_47_prutop_cica_escc_escc_plus() --calculation phase 2 ifrs17.ifrs17_alteration_2_precalculation(integer) ifrs17.ifrs17_alteration_2_api_prusaver_calculation() ifrs17.ifrs17_alteration_2_premium_calculation() --premium phase 2 ifrs17.ifrs17_alteration_premium_11_pruwaiver() ifrs17.ifrs17_alteration_premium_12_pruwaiver33() ifrs17.ifrs17_alteration_premium_18_prupayor() ifrs17.ifrs17_alteration_premium_19_prupayor33() ifrs17.ifrs17_alteration_premium_20_pruspouse_payor() ifrs17.ifrs17_alteration_premium_21_pruspouse_waiver() ifrs17.ifrs17_alteration_premium_22_pruspouse_payor_33() ifrs17.ifrs17_alteration_premium_23_pruspouse_waiver_33() ifrs17.ifrs17_alteration_premium_24_pruparent_payor() ifrs17.ifrs17_alteration_premium_25_pruparent_payor_33_1() ifrs17.ifrs17_alteration_premium_26_pruparent_payor_33_2() ifrs17.ifrs17_alteration_premium_37_pruearly_stage_payor() ifrs17.ifrs17_alteration_premium_38_pruearly_stage_spousepayor() ifrs17.ifrs17_alteration_premium_39_pruearly_stage_parent_payor_1() ifrs17.ifrs17_alteration_premium_40_pruearly_stage_parent_payor_2() | Menggunakan ZPRUPF_V2 sama seperti yang digunakan pada Iteration
Levelized Premium Config Table | IFRS17.IFRS17_MR_COMPONENT IFRS17.IFRS17_RATE IFRS17.IFRS17_HNS_PLAN IFRS17.IFRS17_LEVEL_DEFINITION_PPHPLUS | GP DR (Schema IFRS17)
Premium Counter | STG.LINSPF STG.AGGPPF STG.ZCNTPF | GP DR (Schema STG) | ifrs17.ifrs17_fnc_premium_counter_adhoc_alt(integer) | Menggunakan ZPRUPF_V2 sama seperti yang digunakan pada Iteration
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of iterations
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tables need from GPDR or Postgre Format Schema (tables)
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source of Table
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current stable code in bitbucket

## ETL4 Plan
Iteration | Table | Source | Current Deliverable | Result Table
Iteration 1 | stg.acmvpf | GP DR | etl4_lifeasia | etl4_lifeasia
| stg.rtrnpf | GP DR |  | etl4_lifeasia_invalid
| stg.gtrnpf | GP DR |  | etl4_lifeasia_nonrelated
| stg.genlpf | GP DR |  | etl4_lifeasia_summary
| stg.chdrpf | GP DR
| stg.covrpf | GP DR
| stg.regppf | GP DR
| stg.clmhpf | GP DR
| stg.descpf | GP DR
| stg.covtpf | GP DR
| ifrs17_coa_inscope | GP DR
| ifrs17_param_table_mapping | GP DR
| ifrs17_param_table_mapping_nonrelated | GP DR
| ifrs17_cohort_mapping_table | GP DR
Iteration 2 | tBiilife_Insured_Final | Postgresql | elt4_paylife | etl4_paylife
| incoming_pd (Claim GLIS) | Postgresql |  | etl4_paylife_invalid
| etl4_plai_sungl_mapping | Postgresql
Iteration 3 | MS_POLICY | Postgresql | etl4_pruaman | etl4_pruaman
| MS_CLAIM | Postgresql |  | etl4_pruaman_invalid
| etl4_plai_sungl_mapping | Postgresql
Iteration 4 | MS_POLICY_SHARIA | Postgresql | el4_pruaman_syariah | etl4_pruaman_syariah
| MS_CLAIM_SHARIA | Postgresql |  | etl4_pruaman_syariah_invalid
| MS_REFUND | Postgresql
| etl4_plai_sungl_mapping | Postgresql
Iteration 5 | billing_submission | Postgresql | etl4_omni | etl4_omni
| billing_trx | Postgresql |  | etl4_omni_invalid
| premium_line | Postgresql
| member_product | Postgresql
| policy_member | Postgresql
| member | Postgresql
| person | Postgresql
| product_option | Postgresql
| product | Postgresql
| customer_account | Postgresql
| groups | Postgresql
| policy | Postgresql
| receipt_application | Postgresql
| etl4_plai_sungl_mapping | Postgresql
Iteration 6 | creditshield_premium | Postgresql | etl4_pruemas | etl4_pruemas
| creditshield_claim | Postgresql |  | etl4_pruemas_invalid
| etl4_plai_sungl_mapping | Postgresql
Iteration 7 | pruemas_premium | Postgresql | etl4_creditshield | etl4_creditshield
| pruemas_claim | Postgresql |  | etl4_creditshield_invalid
| etl4_plai_sungl_mapping | Postgresql
Iteration 12 | stg.ptrnpf | GP DR | etl4_gjrev | etl4_gjrev
| etl4_lifeasia | GP DR |  | etl4_gjrev_invalid
| tmp.pdcnpf | GP DR
| tmp.prcnpf | GP DR
| stg.chdrpf | GP DR
| stg.covrpf | GP DR
| TPA_source | GP DR
Iteration 13 | stg.zdcvpf | GP DR | etl4_surrender_report | etl4_surrender_report
etl4_surrender_report_invalid
Iteration 14 | renova_premium | Postgresql | etl4_renova | etl4_renova
| renova_claim | Postgresql |  | etl4_renova_invalid
Iteration 15/Data Lake | stg.zngspf | GP DR | ga_allowance | ga_allowance
| stg.zgodpf | GP DR
| stg.agntpf | GP DR
Iteration 16/Data Lake | stg.rtrnpf | GP DR | bank_charges_policy | bank_charges_policy
| bank_charges_rate | GP DR
Iteration 17 | stg.zrvhpf | GP DR | etl4_lifeasia_missing | etl4_testing_lifeasia
| stg.zglepf | GP DR |  | etl4_testing_lifeasia_invalid
Iteration 18 | stg.itempf | GP DR | etl4_lifeasia | etl4_lifeasia
etl4_lifeasia_invalid
etl4_lifeasia_nonrelated
etl4_lifeasia_summary
Iteration 21 | policy_adj_temp_source | Postgresql | etl4_pat | etl4_pat
etl4_pat_invalid
Iteration 22 | etl4_lifeasia | GP DR | etl4_commission | etl4_commission
| etl4_lifeasia_nonrelated | GP DR |  | etl4_commission_nonrelated
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of iterations
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tables need from GPDR or Postgre Format Schema (tables)
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source of Table
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current stable code in bitbucket

## Sheet1
etl4_lifeasia
elt4_paylife
etl4_pruaman
el4_pruaman_syariah
etl4_omni
etl4_pruemas
etl4_creditshield
etl4_gjrev
etl4_surrender_report
etl4_renova
ga_allowance
bank_charges_policy
etl4_lifeasia_missing
etl4_pat
etl4_commission
etl4_lifeasia
elt4_paylife
etl4_pruaman
el4_pruaman_syariah
etl4_omni
etl4_pruemas
etl4_creditshield
etl4_gjrev
etl4_surrender_report
etl4_renova
ga_allowance
bank_charges_policy
etl4_lifeasia_missing
etl4_pat
etl4_commission

## ETL5 Plan
Iteration | Table | Source | Current Deliverable | Remarks
Iteration 1 | 1. SUNGL IFRS4 Extraction (from Vision Excel - csv format) 2. Exclusion Configuration Table (master data csv format) 3. Finance Configuration Table 4. Bin Account Configuration Table (master data csv format) | 1. SUNGL IFRS4 2. Manual File 3. SUNGL Finance Configuration Table 4. Manual File |  | All Data from IFRS4
Iteration 2 | N/A - Iteration 2 decommissioned | N/A - Iteration 2 decommissioned
Iteration 3 | 1. Policy Statistics 2. Revenue Premium 3. Other Drivers | TBD
Iteration 4 | TBD
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of iterations
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tables need from GPDR or Postgre Format Schema (tables)
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source of Table
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current stable code in bitbucket

## Resources
Name | Role | Team | Status
Akhmad Ghozali | Developer | ETL1
Arief Pradana | Developer | ETL1
Budianto Mahasin | Business Analyst | ETL1
Gusni Kriswin | Business Analyst | ETL1
Gustave Lyman | Developer | ETL1
Selvi Lesmana Putri | Developer | ETL1
Syarif Hidayatullah | Developer | ETL1
Lukas Sahardiman | Developer/Tech Lead | ETL4 | 14 Aug Resign
Ahmad Abdul Matin | Developer | ETL4
Dwiyan Panji | Developer | ETL4
Giok Ty Lagonda | Dev Lead | ETL4/ETL5
Alexander Wardhana | Dev Lead | ETL4/ETL5
Zarot Siagian | Developer | ETL4/ETL5
Arief Zainurrahman | Developer | ETL4/ETL5
Davina Sireg | Business Analyst | ETL5
Miftachul Fadhillah | Business Analyst | ETL4/WDT
Fika Martoprawiro | Dev Lead/PO | ETL4/Data Lake
Fariza Dian Prasetyo | Tech Lead | Data Lake
Muhammad Rizky | Developer | Data Lake
Linnet Sim Li-ling | Developer | Data Lake
Randi Kurnia Pranata | Developer | Data Lake
Frank Zhang | Developer | Data Lake
Jati Wicaksono
Aryanto Willy
Alvin Pratama
Avicenna
Septrio Atma, Yossan
Caesar
Franky

## Org Chart
ETL1 |  | ETL4 |  | ETL5 |  | Datalake
Rendy MO | DO | Alexander W | DO | Giok TY | DO | Fika RUM | PO
Gusni K | BA Lead | Fika RUM | BA Lead | Davina | BA | Rendy Mo | DO
Akhmad G | Dev Lead | Lukas S | Dev Lead | Zarot S | Dev | Fariza DP | Dev Lead
Arief P | Dev | Ahmad AM | Dev | Arief Z | Dev | M Rizky | Dev
Budianto M | BA | Dwiyan P | Dev |  |  | Linnet SLL | Dev
Selvi LP | Dev | Zarot S | Dev |  |  | Randi KP | Dev
Syarif H | Dev | Arief Z | Dev |  |  | Frank Z | Dev
|  | Miftachul F | BA